## Standup Notes
Person | Question | Week: <05/03/2019>
|  | Friday | Saturday | Sunday | Monday | Tuesday | Wednsday | Thursday
Viz | What did you do yesterday? |  | Update on the top level design and involved components | - Freezed on design - Created API Documentation - Created architecture diagram - Implement the menu list GET API as per the design | - Understood the Unit Test suit with serverless framework - Wrote Unit tests for Menu and Card -Tested Menu APIs using Unit tests | - Completed Unite test cases for All APIs - Tested all submitted APIs | Was not available | - Fixed backend defects with end-to-end testing
| What will you work on today? | System design,decide the components to be used with the product. | Freeze the design and draw detailed architecture diagram | - will design Unit Test Suit and start writting Unit tests for APIs | - will finish Unit Tests for other APIs | Not available | Will review end-to-end once | - Continue fixing backend defects if any
| Do you have any obstacles? | No | No | No | No | No | No | No
Nav | What did you do yesterday? |  | - Showed mock screen drawn on paper - Developed the Login page consuming Coginito SDK for successful User Signup and SignIn - Started UI for Add Card | - Completed Add Card UI - Completed UI for transactions and history of transactions - Implemented three APIs, CreateCart, GetCart, UpdateCart | - Completed UI for Cart to order Items - Completed Cart APIs | - Completed UI for Menu Item diaplay and itegrated its flow with Cart UI | - Some UI changes to fix some scenarios | Fixed frontend defects from end-toend testing and some backend changes
| What will you work on today? | Create UI mock up covering all flows of use cases | - develop UI for add card functionality - Develop transaction history page by intergrating with the backend API | - Will add DeleteCart API which will finish all APIs related to Cart - Will work on UI for Cart | - Work on Menu Item UI | - Will do a final touch up to UI and move to Other project tasks | - Deployment of frontend to S3 | Will continue with defect fixing
| Do you have any obstacles? | No | - I will not be able to test Transaction UI till API is developed, but I will write code as per decided design of API | No | No | no | No | No
Dipti | What did you do yesterday? |  | - Could Deploy sample app using serverless framework - Using same step created required Cognito configurations | - Completed the deployment of all components on AWS using serverless framework - All IAM policies are configured using cloudformation template - Completed addToTransaction API | - Implemented GetTransactions API to send the history of transactions | - Completed transaction API and tested with Unit tests | - Woked on presentation - Redeployment with some latest code fixes | - Incorporated team's review comment on documentations
| What will you work on today? | Understand the serverless framework and it's deployment using cloudFormation | - Finish the Deployment as per the componets designed by Viz using same serverless framework - Add all required IAM policies through cloudformation template | - Will continue working on transaction API | - Will complete transaction APIs by adding ClearTransactions API | Will start with prepaing project presentation | - Will incorporate team's review comments on presentation | - Adhoc
| Do you have any obstacles? | No | No | Need Mocks to test APIs | No | No | No | No
Meghana | What did you do yesterday? |  | - Designed DynmoDB Schema for all tables - Understood the DynamoDB deployment using serverless stack refering to sample deployed by Dipti | - Completed YMl scripts for DynamoDB deployment - Integrated with other scripts, DynamoDB tables are getting created with full deployment | - Completed CardCreate and CardGet APIs | Completed Card APIs and tested with Unit tests | - Completed end-to-end testing and raised some defects - Started with deployment diagram | - Completed deployment diagram
| What will you work on today? | Design the schema of dynamoDb tables | - Write YML files to deploy DB using cloudformation template - Will need to work with Dipti to integrate DB scripts with other deployment YML files | - Will start with APIs for Card | - will completeCard APIs | Will do end-end testing using UI | - will continue with deployment diagram and finishing of other documentation | Adhoc
| Do you have any obstacles? | No | Dipti will need to test once DB deployment after integration with Cloudformation scripts | No | No | No | No | no

## XP Values
Communication
Everyone in the team is part of every discussion always. We had daily stand-ups over zoom call every night. The team together discussed and decided on the requirements. The backlog and stories were created during the Zoom meeting and each one of us picked up stories to further break down into tasks. Everyone was clear with overall plan, progress, blockers etc. Any doubts/concerns members prompty started a discussion over WhatsApp team group, which really created the envirment of co-located team. Also, team followed the Scrum board and updated promptly. As interdependencies of tasks were very clear, everyone developed the code keeping those dependencies in mind. This really helped team with fewer bugs and faster delivery.
Feedback
The team followed review practice. Every PR on git was reviewed and commented. This process of review and feedback helped with fewer bugs after deployment. Apart from code, Design of Backend, Front end, Test suit was reviewed. This really helped for getting better at the start itself.