## Backlog
Worktype | Deliverable Area | Work item ID | Product Backlog Items
Precondition | System Frameworks | 1 | System design,decide the components to be used with the product.
Precondition | Integration Model | 2 | Finalize the product architecture.
Precondition | Deployment | 3 | Deploy the architecture designed on AWS
Precondition | Security | 4 | User should be able to SignUp and Signin to application. And Authenticated user should be authorized to access cloud services
Precondition | Lookups | 5 | Create the UI mocks required for the product
Feature | Testing | 6 | Backend should have Unit test suit to verify all the APIs
Feature | Views | 7 | Design Web/mobile UI to support the use-cases in requirement .
Feature | Backend | 8 | Design REST APIs to fullfill the requirement of all use-cases. Use microservices design and develope new API for each functionality
Testing | End-ToEnd Functional testing | 9 | Test the solution using Front end to check all use-case scenarios.
Deliverable | Documentation | 10 | Final Document should be prepared which explains the Design and Functionality of product in detail

## Sprint
Week #1 (10 hrs / week)
Deliverable Area | Backlog Item | User Story | Acceptance Criteria | Task | Task Owner | Initial Estimate (Total Sprint Hours = (3*6) *4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
[7 empty] | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09
[7 empty] | 72 | 60 | 48 | 36 | 24 | 12 | 0 | Ideal Burndown
[6 empty] | 78 | 78 | 60 | 35 | 23 | 13 | 5 | 0 | Remaining Hrs (Total)
System Frameworks | System design,decide the components to be used with the product. | As a architect,all components of the system have to be choosen wisley based on the requirement | 1.All components has to be choosen based on the requirements of the product. 2.Overall a cost effective sytem has to be designed. 3.The system deisgned should be of low coupling and high cohesion. | System design,decide the components to be used with the product. | Viz | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
Integration Model | Finalize the product architecture. | As a architect,system architecture has to be designed effectively | 1.All components has to be choosen based on the requirements of the product. 2.Overall a cost effective sytem has to be designed. 3.The system deisgned should be of low coupling and high cohesion. | Finalize the product architecture. | Viz | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Deployment | Deploy the architecture designed on AWS | Designed architecture has to be delpoyed on AWS. | 1.Intial deployement setup required to start the implementation by other developers has to be done. 2. DB tables should be created as per designed Schema | Deploy the architecture designed on AWS | Dipti | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
|  |  |  | Design and develop the required dynamo db collections using cloudformation scripts | Meghana | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
Security | Setup Authentication and IAM for all AWS services | As a user, he should be able to login to the app.And the access all other services using CongintoID. | 1.Create user pool in AWS cognito through cloud formation script. 2.Once the app is deployed verify the created user pools | Setup cognito user pool to manage login session of the user | Dipti | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Setup IAM policies to authorize Cognito authenticated user to access AWS services | Dipti | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Lookups | Create the UI mocks required for the product | As a user needs a view interact with with the app | 1. The UI Mocks should cover all the designed use cases | Create UI mock up covering all flows of use cases | Nav | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Unit Testing | Backend should have Unit test suit to verify all the APIs | As a develper, I should be able to test the backend APIs independent of frontend | 1. Unit tests should call all REST APIs 2. Developer should be able to test APIs locally as well as invoke on AWS 3. The request and response of APIs should be handled as expected in uni tests | Implement Unit Tests for all Card related APIs | Viz | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  |  | Implement Unit Tests for Menu Item related APIs | Viz | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
|  |  |  | Implement Unit Tests for Cart Item related APIs | Viz | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  |  |  | Implement Unit Tests for Transaction related APIs | Viz | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Views | Design Web/mobile UI to support the use-cases in requirement | As a user, he should be able to login smoothly from the login screen | 1.Once the user launches the app,he should see the prodcut name on the page. 2.Login page should have email and password enter text space. 3.Once the credentilas entered, he should have button to click login | Develop the Login page consuming Coginito SDK for successful User Signup and SignIn | Nav | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a view, it should perform add card operation for the user in the UI | 1.Once the user launch the app,he should see the prodcut name on the page. 2.On successful login,he should land to home page. 3.In home page user should have a button to add card to his account. | Design and develop UI for add card functionality | Nav | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
|  | As a view, it should display transcation history for the user in the UI | 1.Once the user launch the app,he should see the prodcut name on the page. 2.On successful login,he should land to home page. 3.In home page user should have a button to see history of transactions. 4.On click of history button he should have all transactions listed in the browser. | Develop transaction history page by intergrating with the backend API | Nav | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | As a logged in user I should have user friendly views to order items. | 1.Once the user launch the app,he should see the prodcut name on the page. 2.On successful login,he should land to home page. 3.In home page user should have a button to order items. 4.On click of order button he can choose the menu items interested. 5.If the user has balance to pay fro the item, the order should be succesful | Design UI views to order an item. | Nav | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  | As a user I should get list of menu items to choose before ordering. | 1.Once the user launch the app,he should see the prodcut name on the page. 2.On successful login,he should land to home page. 3.In home page user should have a button to order items. 4.On click of order button he can choose the menu items interested. | Display the menu items in the UI, when user touches order button | Nav | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
BackEnd | Design REST APIs to fullfill the requirement of all use-cases. Use microservices design and develope new API for each functionality | As a web service, card REST APIs should allow user to perform all operations associated with card. | 1. API for ADD card should add new card in DB linked to user 2.API for UPDATE card should update the card attributes stored inn DB 3. API GET Card should return all Card attributes stored in DB. 4. All APIs should return proper return codes like 200, 500. 5. The response of each API should be in JSON format. | Implement the Add card API-POST call | Meghana | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  |  | Implement API-GET call to retrieve User's Card information | Meghana | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  |  | Implement API-UPDATE to update User's Card details | Meghana | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  |  |  | Implement API-DELETE to delete the card for User | Meghana | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | As a web service, menu REST APIs should allow user to perform all operations associated with DB table storing Menu Item List. | 1.The API should be implemented with GET functionality 2.API should return back list of menu items. 3.Menu items returned should match the list menu list contents of DB. 4.Once the call is succesfull the call should return 200 status. | Implement the menu list GET API.This API should fetch the list of menu items from menu database | Viz | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | As a web service, transaction functionality should be exposed with all CRUD operations to update the logged in user with transction details | 1.The API should be implemented with CRUD opertaions. 2.API should provide the transaction detials matching the DB contents. 3.Once the call is succesfull the call should return 200 status. | Implement POST-API to complete transaction | Dipti | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | Implement GET-API to retrieve History of transactions | Dipti | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  |  | Implemet DELETE-API to clear history of transactions | Dipti | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | As a web service, Cart functionality should be exposed with all CRUD operations to update the logged in user with transction details | 1.The API should be implemented with CRUD opertaions. 2.API should provide the Cart detials matching the DB contents. 3.Once the call is succesfull the call should return 200 status. | Implement POST-API to create new Cart for user. | Nav | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Implement UPDATE-API to add Items to User Cart. | Nav | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Implement GET-API to Get User Cart. | Nav | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Implement DELETE-API to delete User Cart after successful transaction. | Nav | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
End-ToEnd Functional testing | Test the solution using Front end to check all use-case scenarios | As a tester, I should be able to perfom operations covering all use-case scenarios from requirement | 1. New user should be able to Sign-Up and then sign-In 2. User should be able add new card as well as update existing Card 3. Once user orders a menu Item, it should be added to Cart 4. On successful transaction, the Card balance should be deducted and Cart should be emptied. 5. user should be able to view the history of all previous transactions | Test all operations provided on UI. Make sure that cobvers all Use-cases from requirement | Meghana | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Documentation | ReadMe and Project presentation should cover all important details | End user should be able to understand Deployment, use cases, design after refering to documentation | 1. As a product user i should be able to install product by following steps in ReadMe 2. As a end user, I should be able to understand overall design and functionality from presentation | Prepare Deployment diagram | Meghana | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  |  |  | Prepare Project presentation | Dipti | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
BugFixing | All priority bugs from testing should be fixed | The tster should be able to run all priority use-cases without any issue | 1. All priority scenarios should work as expected 2. All fixes should get merged with main branch | Fix defects at backend | Viz | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
|  |  |  | Fix defects at front end | Nav | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0
| Team: |  |  |  | Viz | 21
| Viz | 3 hours / day | 18 Hours / week |  | Nav | 22
| Nav | 3 hours / day | 18 Hours / week |  | Dipti | 18
| Dipti | 3 hours / day | 18 Hours / week |  | Meghana | 17
| Meghana | 3 hours / day | 18 Hours / week |  | Total | 78
| Total Available Hours During Sprint: |  | 72